**Jump2it! Dance Festival** *2019*

Schedule of events – draft version

Week beginning

|  |  |  |  |
| --- | --- | --- | --- |
| 26 | 24th Sept | Launch event 1 – meeting with school representatives | |
| 25 | 1st Oct |  | |
| 24 | 8th Oct | Schools to confirm which class will be taking part in the festival | |
| 23 | Half term | | |
| 22 | 22nd Oct |  | |
| 21 | 29th Oct |  | |
| 20 | 5th Nov |  | |
| 19 | 12th Nov |  | |
| 18 | 19th Nov | Schools to receive confirmation of   * Dates of rehearsals * Times of rehearsal * the book their dance will be based on | |
| 17 | 26th Nov | Posters to print | |
| 16 | 3rd Dec | Launch event 2 – with the children  Performance at Cedars Academy – times TBC  All festival schools attend | |
| 15 | 10th Dec |  | |
| 14 | 17th Dec |  | |
| 13 | Christmas break | | |
| 12 | Christmas break | | |
| 11 | 7th Jan | Rehearsals start with dance artist  block 1 schools | Posters given out to block 1 schools |
| 10 | 14th Jan | Rehearsal with dance artist  block 1 schools |  |
| 9 | 21st Jan | Rehearsal with dance artist  block 1 schools | Ticket letters go out |
| 8 | 28th Jan | Rehearsals start with dance artist  block 2 schools | Ticket letters go out  Posters given out to block 2 schools |
| 7 | 4th Feb | Rehearsal with dance artist  block 2 schools | **Tickets go on sale** |
| 6 | 11th Feb | Rehearsal with dance artist  block 2 schools | Class photo and names deadline for programme and bus seats |
| 5 | Half term | | |
| 4 | 25th Feb | Schools to arrange rehearsals with their class | Programmes go to print |
| 3 | 4th March | Final rehearsal with dance artist  block 1 schools |  |
| 2 | 11th March | Final rehearsal with dance artist block 2 schools | Programmes arrive |
| 1 | 18th March | Schools to arrange final rehearsal with full costume and props | Bus timetable sent out to schools |
|  | 25th March | **Jump2it! Performance at LTH** |  |